## Plan
90 day marketing plan
Put the start date and each task's due date is calculated from its week number.
Start date
Phase | Week | Task | Owner | Due | Status
Base | 1 | Write the message house and run the five second test |  |  | To do
Base | 1 | Record the first six numbers in the metrics calculator |  |  | To do
Base | 2 | Photograph the pieces with six shots each |  |  | To do
Base | 2 | Rewrite the product pages and fix the top three store issues |  |  | To do
Base | 2 | Add the sign up form to the store and the bio |  |  | To do
Attention | 3 | Fill the content calendar and shoot the first batch |  |  | To do
Attention | 3 | Post three to four times this week |  |  | To do
Attention | 4 | Write the three welcome messages and switch them on |  |  | To do
Attention | 4 | Choose five creators and send the messages |  |  | To do
Attention | 5 | Ask the first five customers for feedback and collect photos with permission |  |  | To do
Attention | 6 | Review content: which pillar earned the most shares? |  |  | To do
Attention | 7 | Improve category pages and titles for search |  |  | To do
Attention | 8 | Write the post purchase message and the back in stock alert |  |  | To do
Growth | 9 | Prepare three ad ideas and set the test budget |  |  | To do
Growth | 10 | Run the test and log the results |  |  | To do
Growth | 11 | Try one offer (a bundle or a gift) and measure its effect |  |  | To do
Growth | 12 | Write the line sheet and contact five boutiques |  |  | To do
Growth | 13 | A small drop to your list first, then review all thirteen weeks |  |  | To do
Progress

## Weekly dashboard
Weekly dashboard: ten minutes every Sunday
Enter the week's numbers and the ratios are calculated. Then note what worked, what you will stop and your one key step.
Week | Starts | Visitors | Orders | Sales | Marketing spend | New customers | Returning customers | Conversion | AOV | CAC | Repeat rate | What worked | What we stop | Next week's step
1
2
3
4
5
6
7
8
9
10
11
12
13
Total