## Plan
90 day private label plan
Put the start date and the due dates are calculated from the week number.
Start date
Phase | Week | Task | Due | Status
Base | 1 | Choose the model and fill the niche scorecard |  | To do
Base | 2 | Talk to ten potential customers |  | To do
Base | 3 | A shortlist of five pieces and three suppliers |  | To do
Development | 4 | Vet the suppliers and ask about exclusivity |  | To do
Development | 5 | Request samples and write the customisation brief |  | To do
Development | 6 | Assess the samples and comment point by point |  | To do
Development | 7 | Work out cost and pricing at three quantities |  | To do
Development | 8 | Set the first quantity, the cash plan and the reorder point |  | To do
Launch | 9 | The compliance checklist and brand registration |  | To do
Launch | 10 | The purchase order, quality spec and AQL |  | To do
Launch | 11 | Labels, packaging and photography |  | To do
Launch | 12 | Pre shipment inspection and the first sales channel ready |  | To do
Launch | 13 | Launch and a review of the 13 weeks |  | To do
Progress

## Supplier comparison
Private label supplier comparison
Compare suppliers on minimums, exclusivity, sample and communication.
Supplier | Product | Product MOQ | MOQ with customisation | Exclusivity | Sample cost | Sample days | Sample quality (1-5) | Communication (1-5) | Score (out of 10) | Decision