## Samples
Sample tracker
Log each round, its dates and your decision.
Supplier | Stage | Requested | Received | Days | Sample and shipping cost | Decision | Comments, point by point
Total sample cost

## Production
Production follow up
Put the purchase order date and the milestone dates are calculated.
Purchase order date
Milestone | Days after PO | Due | Status | Notes
Approve the pre production sample and pay the deposit | 3 |  | To do
Fabric and trims arrive, with photos | 14 |  | To do
Cutting and sewing start | 18 |  | To do
Mid production: photos and early check | 28 |  | To do
Production finished | 38 |  | To do
Final inspection and illustrated report | 40 |  | To do
Second payment and hand over to shipping | 42 |  | To do
The days are an illustrative example. Plan around the Lunar New Year holiday.

## 90 day plan
90 day sourcing plan
Put the start date and due dates are calculated from the week number.
Start date
Phase | Week | Task | Due | Status
Base | 1 | Write the sourcing brief and the target cost |  | To do
Base | 2 | Build a long list of ten suppliers from two channels |  | To do
Base | 3 | Send the RFQ to five suppliers |  | To do
Vetting | 4 | Read the offers and compare them on landed cost |  | To do
Vetting | 5 | Vet the best three and fill the scorecard |  | To do
Vetting | 6 | Order the first samples and track time |  | To do
Vetting | 7 | Comment on the samples point by point |  | To do
Vetting | 8 | Negotiate and choose the supplier |  | To do
Commitment | 9 | Write the purchase order, payment schedule and NDA |  | To do
Commitment | 10 | First payment and production start |  | To do
Commitment | 11 | Follow production with photos and book the inspection |  | To do
Commitment | 12 | Final inspection and shipping paperwork with the broker |  | To do
Commitment | 13 | Second payment, shipping and a review of the 13 weeks |  | To do
Progress